## Slide 1
Sprint Planning
Team Based Project ( MOD008917 )

## Slide 2: The Sprint Planning Process
How much available working time do we have?
How complicated is the work we have to do?
Assign work into the available time.

## Slide 3: Available Time (Per Person)
Assume an average working week: 35-37 hours.
Remove class time for all classes during the week.
Remove travel time.
Remove time for any regular appointments or family commitments.
Divide the remainder of the time between modules. (e.g. 10 hours over 3 modules but 4 lessons = 2.5hrs, 2.5hrs, and 5hrs)
Multiple time for the module by 0.8 (80%) to apply a buffer.

## Slide 4: Available Time (Example)
37 hours.
37 – 12 hours class = 25 hours.
25 – (3 journeys, 0.5 hrs each way) = 22 hours.
22 – 2 hours per day = 12 hours.
12 hours over 3 modules but 4 lessons = 3 hours per lesson.
Team Based is a double lesson = 6 hours.
6 hours x 0.8 = 4.8 hours per week.

## Slide 5: Estimated Workload
There is a software estimation technique called “Planning Poker” where all people in a team use cards from 1-5 to rate the effort for any particular task.
Create Title Slide (1pt)
Assemble 3 Slides Into 1 (2pt)
Animate All Slides (3pt)
Research Content For Slides (4pt)
Learning New Coding Language (5pt)
Convert Slides to Program (??? pts)
For unknown quantities, assign 5pts initially and reassess later if necessary or you can split it into smaller tasks.

## Slide 6: Fill The Sprint
This is the stage where you fill the sprint backlog from the project backlog based on the total available time across the entire team.
1 story point = 1 hour or less.
5 story points = 5 hours or more.
Because story points don’t align directly to hours, you can assign more story points to a person than they have hours. For the first sprint:
No member of the team should have more than one 5-pointer.
No member of the team should have more than 10-points total.

## Slide 7: Future Sprints
After the first sprint, you get better at estimating.
You can remove points from future sprints or add more in if you have time.
Each time you will improve.

## Slide 8: Update The Kanban Board
Backlog
Sprint
In Dev
Ready For Test
In Test
Done
Task 5
Task 6
Task 7
Task 8
Task 1
Task 2
Task 3
Task 4
Task 10
Task 9